## Copy of Google
ID | Date | Phase | Task | Details / done when | Owner | Blocks go-live? | Depends on | Status | Done on | Notes | Ref
G01 | Mon 28 Sep | Website | Remove the Rs 5,999 menu item sitewide | "Register Company for Just ₹5999" gone from menu and footer on every page. Can go live immediately | Pragaman | Yes | T3 | Not started |  |  | G§1 #1
G02 | Mon 28 Sep | Website | Company registration page at ₹2,999 + GST (staging) | Title, H1, hero and full pricing table at "₹2,999 + GST professional fee" for every company type; six inclusions above the fold; footnote "Government fees, stamp duty and DSC extra"; 4.8 changed to 4.7 | Pragaman | Yes | T3 | Not started |  |  | G§1 #2, #8
G03 | Mon 28 Sep | Website | Startup India page rebuilt (staging) | H1 "Startup India (DPIIT) Recognition Certificate"; price block; what we do; documents needed; "An expert will call to check your eligibility"; FAQ 8 reframed; "minimal fees" removed; tax-holiday wording fixed; title typo; 5,000+ line; "No company yet?" block | Pragaman | Yes | T3 | Not started |  |  | G§1 #3-5, #10, #12
G04 | Mon 28 Sep | Website | LLP and OPC pages at ₹2,999 + GST (staging) | Needed only for two price-asset items; if not ready, drop those two items | Pragaman | No | T3 | Not started |  |  | G§4
G05 | Mon 28 Sep | Website | Private-firm line near the form on both pages | "Filing Buddy is a private professional services firm, not affiliated with DPIIT, MCA or the Government of India." | Pragaman | Yes | T3 | Not started |  |  | G§1 #7
G06 | Mon 28 Sep | Website | Calendar buttons point to the on-page form | "Book a Call now", "Start Your Company Registration", "Register Your Company Online Today" scroll to the form (or bookings tracked as a conversion) | Pragaman | Yes | T3 | Not started |  |  | G§1 #6
G07 | Mon 28 Sep | Tracking | Fix conversion trigger if T2 showed it fires before OTP | dataLayer event on OTP success; GTM trigger moved to it. If NO conversion fires at all on a page, this becomes a launch blocker | Pragaman | No | T2 | Not started |  |  | G§7A
G08 | Mon 28 Sep | Google Ads | Confirm auto-tagging is ON | Admin > Account settings > Auto-tagging | Pragaman | Yes |  | Not started |  |  | G§7B
G09 | Mon 28 Sep | Google Ads | Create the seven shared negative lists | NEG_Brand, NEG_Competitors, NEG_Other_Brands, NEG_Out_of_scope, NEG_G2_only, NEG_G1_only, NEG_G1_status (terms in spec) | Pragaman | Yes |  | Not started |  |  | G§3
G10 | Mon 28 Sep | Google Ads | Build G1_StartupIndia_2999 (PAUSED) | Search only (Display and Search Partners off); current 19 cities, presence; Maximize conversions; Rs 1,700/day; lead form + call primary; AI Max off; final URL suffix with UTMs; ad groups SI_Certificate, SI_DPIIT, SI_StartupRegistration with keywords (phrase and exact only) | Pragaman | Yes | G09 | Not started |  |  | G§2, G§3
G11 | Mon 28 Sep | Google Ads | G1 ads: two RSAs per ad group | RSA A price-led, one keyword headline pinned to position 1; RSA B trust-led, nothing pinned; from the headline and description bank | Pragaman | Yes | G10 | Not started |  |  | G§4
G12 | Mon 28 Sep | Google Ads | Build G2_CompanyReg_2999 (PAUSED) with ads | Same settings; Rs 1,325/day; ad groups CR_PvtLtd and CR_Generic; keywords; two RSAs per ad group (A pinned, B unpinned) | Pragaman | Yes | G09 | Not started |  |  | G§2-4
G13 | Mon 28 Sep | Google Ads | Attach negative lists | All four common lists to G1 and G2; NEG_G1_only and NEG_G1_status to G1; NEG_G2_only to G2; NEG_Brand to Competitor | Pragaman | Yes | G10, G12 | Not started |  |  | G§3
G14 | Mon 28 Sep | Google Ads | Account assets | 5 sitelinks; callouts incl. "Calls 9 AM to 6:30 PM" and "5,000+ Companies Formed"; structured snippet; price asset with 4 items (Pvt Ltd, LLP, OPC, Startup India, each ₹2,999, "+GST, govt fees extra"); call asset scheduled 9:00 AM to 6:30 PM on the days from T4; logo | Pragaman | Yes | T4 | Not started |  |  | G§4
G15 | Tue 29 Sep | Google Ads | Image assets | 1.91:1 and 1:1 crops from the statics: G1 Startup India and Process concepts; G2 Price and Trust concepts | Pragaman | No | T1 | Not started |  |  | G§4
G16 | Tue 29 Sep | Google Ads | Prepare Competitor and Brand price edits (do not post) | Every RSA with 1,999, 5,999 or 2,999 without GST rewritten to "₹2,999 + GST"; saved as drafts in Google Ads Editor | Pragaman | Yes |  | Not started |  |  | G§4
G17 | Tue 29 Sep | Google Ads | Check ad review on G1 and G2 | Ads in paused campaigns are reviewed; fix any disapproval; note the label behind "approved (limited)" | Pragaman | Yes | G11, G12 | Not started |  |  | G§8
G18 | Tue 29 Sep | Website | Staging review of G02-G06 | Open each staged page on mobile: price, extras, disclosure, form works | Pragaman | Yes | G02-G06 | Not started
G19 | Tue 29 Sep | Sales | Disposition sheet columns for Google leads | Add "quoted price" and "product" (company registration or Startup India) | Pragaman | No |  | Not started |  |  | G§7D
G20 | Tue 29 Sep | Check | Pre-launch check | Every Yes row above is Done; if not, launch moves to Thu 1 Oct | Pragaman | Yes | All above | Not started |  |  | Start here
G21 | Wed 30 Sep | Launch | Publish the staged pages | Site shows ₹2,999 + GST; no 1,999 or 5,999 anywhere | Pragaman | Yes | G20 | Not started |  |  | G§8
G22 | Wed 30 Sep | Launch | Enable G1 and G2 | Immediately after G21 | Pragaman | Yes | G21 | Not started
G23 | Wed 30 Sep | Launch | Pause Tier1 and Tier2 | Search_Comp_reg_tier1_exact_phrase and _tier2_. Never unpause Tier1 (1,738 broad keywords) | Pragaman | Yes | G22 | Not started
G24 | Wed 30 Sep | Launch | Post the Competitor and Brand price edits | From G16 drafts | Pragaman | Yes | G21 | Not started
G25 | Wed 30 Sep | Launch | Brand changes | Budget 500 to 300; bid strategy Target impression share, top of page 90%, max CPC Rs 70; pause broad keyword "filing buddy consultants private limited" | Pragaman | No |  | Not started |  |  | G§5, G§6
G26 | Wed 30 Sep | Launch | Competitor budget 1,500 to 900 | Nothing else changes (D7 review running) | Pragaman | No |  | Not started |  |  | G§5
G27 | Wed 30 Sep | Launch | Live form test on both pages | Submit one lead on each page; conversion appears in Google Ads within about 3 hours | Pragaman | Yes | G21 | Not started
G28 | Wed 30 Sep | Launch | Live call test | Call through the ad's call extension between 9:00 AM and 6:30 PM; appears under phone calls | Pragaman | No | G22 | Not started
G29 | Wed 30 Sep | Launch | Tell the Agent launch is done | Time of each step, so state can be updated and clocks started | Pragaman | No |  | Not started
G30 | 1-6 Oct | Watch | Daily watch, no optimisation | Pacing 50-150% of budget; approvals; conversions firing. Rs 3,000+ spend with 0 conversions = tracking check, not a bid change | Pragaman | No |  | Not started
G31 | Mon 5 Oct | OPS RUN | First OPS RUN | Share G_Campaigns (last 7 days) and attach G_SearchTerms (last 7 days) in chat | Pragaman | No |  | Not started
G32 | Wed 14 Oct | OPS RUN | Day-14 checkpoint (D10) | Search terms and negatives; RSA A vs B; budget moves inside the envelope; ad schedule; call threshold. Share 14-day exports | Pragaman | No |  | Not started |  |  | G§9
G33 | Fri 23 Oct | Review | Competitor review and geo | D7 keep or stop; location report on G1 and G2; AI Max test decision for G2; all-India test for G1 | Pragaman | No |  | Not started |  |  | G§8
G34 | From 30 Oct | Phase 2 | Offline conversions | Upload qualified and won leads back to Google Ads (needs gclid on each lead, dev brief item 7) | Pragaman | No |  | Not started |  |  | G§7C