## Copy of Meta
ID | Date | Phase | Task | Details / done when | Owner | Blocks go-live? | Depends on | Status | Done on | Notes | Ref
M01 | Mon 28 Sep | Creatives | Statics final | Agent review from T1 done; price reads "₹2,999 + GST"; nothing says 1,999 or 5,999; concepts 1 Price, 2 Process, 3 Trust in 1:1, 4:5 and 9:16 | Creative | Yes | T1 | Not started |  |  | M§5
M02 | Mon 28 Sep | Form | Build FB_Form_2999_Quality | Higher intent; intro "Register your company: ₹2,999 + GST" with inclusions and "Government fees, stamp duty and DSC are extra"; Full name, Phone, Email, City; Q1 What would you like to register? (Private Limited / LLP / OPC / Startup India (DPIIT) / Not sure yet); Q2 When do you want to start? (Within a week / Within a month / Just exploring); privacy link; completion text with 9:00 AM to 6:30 PM and next-morning line | P | Yes |  | Not started |  |  | M§4
M03 | Mon 28 Sep | Form | Connect the form to the Google Sheet | Meta's own integration, as today | P | Yes | M02 | Not started
M04 | Mon 28 Sep | Form | Test lead | Submit a test lead; the sheet shows campaign, ad set, ad names, Q1 and Q2. If ad names are missing, set a weekly lead download for the Agent | P | Yes | M03 | Not started |  |  | M§4
M05 | Mon 28 Sep | Sales | Lead sheet columns | Add: quoted price; first-call time; reach status (Reached / No answer / Wrong or invalid number); qualified status | Sales | No | M03 | Not started |  |  | M§6
M06 | Mon 28 Sep | Campaign | Build FB_2999_Leads_30Sep (PAUSED) | Objective Leads; instant form; Maximize number of leads; no cost cap; budgets at ad set level | P | Yes |  | Not started |  |  | M§2
M07 | Mon 28 Sep | Campaign | Ad set AS_A_Cities | 16 cities at: Chandigarh +10 mi, Delhi +19, Ahmedabad +10, Vadodara +10, Kochi +10, Mumbai +23, Pune +12, Bangalore +14, Bhubaneswar +10, Jaipur +10, Chennai +18, Coimbatore +10, Kolkata +10, Patna +10, Indore +10, Hyderabad +12. Advantage+ audience, same 14 suggestions, age 24-50; Advantage+ placements, no exclusions; Rs 1,500/day | P | Yes | M06 | Not started |  |  | M§2
M08 | Mon 28 Sep | Campaign | Ad set AS_B_RestOfIndia | India, EXCLUDING exactly the same 16 cities at exactly the same radii as AS_A; same audience and placements; Rs 2,000/day | P | Yes | M07 | Not started |  |  | M§2
M09 | Tue 29 Sep | Ads | Three statics in AS_A | Concepts 1, 2, 3 with placement asset customisation (1:1, 4:5, 9:16); headline, primary text and description from the plan; CTA Apply now; form FB_Form_2999_Quality; names like AS_A ¦ C1_Price ¦ Static | P | Yes | M01, M02, M07 | Not started |  |  | M§5
M10 | Tue 29 Sep | Ads | Same three ads in AS_B by post ID | Use existing post, so likes and comments pool; names AS_B ¦ ... | P | Yes | M09 | Not started |  |  | M§2
M11 | Tue 29 Sep | Ads | Submit for review and check approvals | Fix any rejection before Wed | P | Yes | M10 | Not started
M12 | Tue 29 Sep | Sales | Brief sales | New-form leads are ₹2,999 + GST; old-form leads submitted before the switch keep ₹1,999; call "Within a week" first; fill reach status on every lead | P | Yes |  | Not started
M13 | Tue 29 Sep | Creatives | Brief the concept 2 video | 15-30 s; 9:16 plus 4:5; captions; readable without sound; price and extras on screen. Needed by Mon 5 Oct | P | No |  | Not started |  |  | M§5
M14 | Wed 30 Sep | Launch | Enable FB_2999_Leads_30Sep | Only after the website shows ₹2,999 + GST (Google G21) | P | Yes | G21, M11 | Not started
M15 | Wed 30 Sep | Launch | Turn off Static Ad 1,999 | Same hour as M14. Do not touch the Instagram boosts | P | Yes | M14 | Not started
M16 | Wed 30 Sep | Launch | First leads check | First real leads arrive in the sheet with ad names and both answers | P | Yes | M14 | Not started
M17 | 1-6 Oct | Watch | Daily watch, no edits | Delivery; CPL alert above Rs 150 on Rs 3,000+ spend; leads in the sheet; reach rate | P | No |  | Not started
M18 | Mon 5 Oct | OPS RUN | First OPS RUN | Share M_Ads (last 7 days, by ad) and the lead sheet export | P + Agent | No |  | Not started
M19 | Wed 7 Oct | Step 1 | Budget step 1 and video (if trigger met) | Trigger: CPL at or below Rs 150 on Rs 3,000+ in the prior 7 days and reach rate not falling. Then AS_B 2,400, AS_A 1,800, and add the concept 2 video to both ad sets the same day. If missed, hold one week | P | No | M13, M18 | Not started |  |  | M§3
M20 | Mon 12 Oct | Creatives | Carousel ready | Concept 5 What's included: 1:1 cards, one per inclusion, last card price and extras | Creative | No |  | Not started |  |  | M§5
M21 | Wed 14 Oct | Step 2 | Budget step 2 and carousel (if trigger met) | Same trigger on the 7 days after step 1. AS_B 2,500, AS_A 2,000; add the carousel; pause the weakest static. Day-14 read on CPL, reach rate, qualified rate, answer mix | P + Agent | No | M19, M20 | Not started |  |  | M§3, M§7
M22 | Wed 21 Oct | Test | Startup India ad set | AS_D_StartupIndia, Rs 600/day from inside the budget, concept 4, same form; only if AS_A and AS_B are stable | P | No | M21 | Not started |  |  | M§5
M23 | From 30 Oct | Phase 2 | Lead-quality feedback to Meta | Scope sending sales outcomes back to Meta (conversion leads), once reach and qualified status are filled on every lead | P + Agent | No | M05 | Not started |  |  | M§6