## Tasks
Date | Day | Task | Owner | Type | Critical path | Done | Status | Notes
2026-09-14 | Mon | Send Shlok the brand kit: logo in colour, white and black, as PNG and SVG, plus the brand font | Pragaman | Setup | Yes | Yes | Done
2026-09-14 | Mon | Send Shlok the Filing Buddy report and confirm the approved proof line: 1,000+ clients delivered | Pragaman | Setup | Yes | No | OVERDUE
2026-09-14 | Mon | Remove current clients and team from the cleaned CA list CSV, and decide on the 6 flagged contacts | Pragaman | Ads | Yes | Yes | Done
2026-09-14 | Mon | Upload the CSV as NW_CA_LIST_Network in Ads Manager (matching takes up to 24 hours) | Pragaman | Ads | Yes |  | OVERDUE
2026-09-14 | Mon | Build the lead form NW_CA_Form_v1: intro, 4 questions, privacy link, thank-you screen with Aryan's number | Pragaman | Ads | Yes |  | OVERDUE
2026-09-14 | Mon | Send a test lead through the Lead Ads Testing Tool and confirm it reaches the lead tracker | Pragaman | Ads | Yes |  | OVERDUE
2026-09-14 | Mon | Draft ST01 and ST02 in both sizes | Pragaman | Design | Yes |  | OVERDUE
2026-09-14 | Mon | Draft ST03 and ST04 in both sizes | Shlok | Design | Yes |  | OVERDUE
2026-09-14 | Mon | Create the Drive folders 00 to 07, upload both trackers, set the Sheets locale to India, share with the team | Pragaman | Setup |  |  | OVERDUE
2026-09-14 | Mon | Confirm the Thu 24 Sep shoot in Anjan's calendar and ask him to bring a festive outfit for the Diwali wish | Pragaman | Setup |  | No | OVERDUE
2026-09-14 | Mon | Confirm Aryan's working hours and the 2-working-hour reply window, then update the lead tracker Settings tab | Pragaman | Leads |  |  | OVERDUE
2026-09-14 | Mon | Set up WhatsApp Business: profile, greeting, away message, quick replies, labels | Aryan | Leads |  |  | OVERDUE
2026-09-15 | Tue | Peer review all four statics by 12 PM (Pragaman reviews Shlok's, Shlok reviews Pragaman's) | Pragaman | Review | Yes |  | OVERDUE
2026-09-15 | Tue | Anjan approves ST01 to ST04 at 5 PM, and log the result in the creative tracker | Anjan | Approval | Yes |  | OVERDUE
2026-09-15 | Tue | Check the CA list match status and note the matched size | Pragaman | Ads | Yes |  | OVERDUE
2026-09-15 | Tue | Create NW_CA_EXCL_Submitted_180d and NW_CA_RET_FormOpen_60d from the lead form | Pragaman | Ads | Yes |  | OVERDUE
2026-09-15 | Tue | Upload NW_CA_EXCL_Blocklist with current clients and Noboru team members | Pragaman | Ads | Yes |  | OVERDUE
2026-09-15 | Tue | If 100 or more matched, build the 1% India lookalike NW_CA_LAL1_IN_Network. If fewer, skip it and note it | Pragaman | Ads |  |  | OVERDUE
2026-09-15 | Tue | Save the NW CA Weekly column preset in Ads Manager | Pragaman | Ads |  |  | OVERDUE
2026-09-15 | Tue | Check Account Quality is clean and two Business Manager admins have two-factor authentication | Pragaman | Admin |  |  | OVERDUE
2026-09-15 | Tue | Turn on comment moderation and spam keyword filters on the Facebook Page and Instagram | Pragaman | Admin |  |  | OVERDUE
2026-09-15 | Tue | Book the shoot room and plan the test shoot for Tue 22 Sep | Shlok | Shoot |  |  | OVERDUE
2026-09-16 | Wed | Export finals ST01 to ST04 in 1080x1350 and 1080x1920, run the pre-export checklist, save to the Finals folder | Pragaman, Shlok | Design | Yes |  | OVERDUE
2026-09-16 | Wed | Build the prospecting campaign NW_CA_PROS_Leads_Sep26, scheduled to start 18 Sep 12:00 AM | Pragaman | Ads | Yes |  | OVERDUE
2026-09-16 | Wed | Set the ad set: instant forms, maximise leads, India, minimum age 25, exclusions in Audience controls | Pragaman | Ads | Yes |  | OVERDUE
2026-09-16 | Wed | Turn off Audience Network, Messenger, Marketplace, right column and search results placements | Pragaman | Ads | Yes |  | OVERDUE
2026-09-16 | Wed | Upload the four ads with both sizes, approved copy, Get quote CTA and NW_CA_Form_v1 attached | Pragaman | Ads | Yes |  | OVERDUE
2026-09-16 | Wed | Switch off creative enhancements that change text or visuals, and switch off multi-advertiser ads | Pragaman | Ads | Yes |  | OVERDUE
2026-09-16 | Wed | Submit the ads for review (review usually takes under a day) | Pragaman | Ads | Yes |  | OVERDUE
2026-09-16 | Wed | Update all four creatives to Final in the creative tracker | Pragaman | Admin |  |  | OVERDUE
2026-09-17 | Thu | Recharge Meta with Rs 30,000 and note the usable balance after GST | Pragaman | Ads | Yes |  | OVERDUE
2026-09-17 | Thu | Confirm all four ads show Approved. If any is rejected, soften the wording, keep T&C apply, and resubmit | Pragaman | Ads | Yes |  | OVERDUE
2026-09-17 | Thu | Run the full pre-launch QA checklist from the Meta Ads Campaign Guide, section 13 | Pragaman | Review | Yes |  | OVERDUE
2026-09-17 | Thu | Finish the scripts for VD01, VD02a to VD02e and VD07, and the copy for ST05 and CR01 | Pragaman | Copy | Yes |  | OVERDUE
2026-09-17 | Thu | Set calendar reminders for the next recharges on 8 Oct and 3 Nov | Pragaman | Admin |  |  | OVERDUE
2026-09-17 | Thu | Preview each ad on Instagram Feed, Stories and Reels and check nothing is cropped | Pragaman | Review |  |  | OVERDUE
2026-09-17 | Thu | Schedule the organic posts for 18, 21, 23 and 25 Sep with captions and hashtags | Pragaman | Post |  |  | OVERDUE
2026-09-17 | Thu | Brief Aryan: where leads land, the follow-up steps, grading, and the WhatsApp opener | Pragaman | Leads |  |  | OVERDUE
2026-09-18 | Fri | Campaign goes live at 12:00 AM. Confirm delivery is Active in the 11 AM check | Pragaman | Ads | Yes |  | OVERDUE
2026-09-18 | Fri | Send the scripts and copy to Anjan and Shlok, and ask Anjan to review before Tue 22 Sep | Pragaman | Copy | Yes |  | OVERDUE
2026-09-18 | Fri | ST01 posts in the evening. Reshare to Stories | Pragaman | Post |  |  | OVERDUE
2026-09-18 | Fri | No edits to the campaign until 25 Sep, so Meta can finish learning | Pragaman | Ads |  |  | OVERDUE
2026-09-21 | Mon | Post ST02 | Pragaman | Post |  |  | OVERDUE
2026-09-21 | Mon | Weekly review 1, read only: delivery, first leads, reply times. Make no changes | Pragaman | Review |  |  | OVERDUE
2026-09-22 | Tue | Anjan approves the scripts at 5 PM | Anjan | Approval | Yes |  | OVERDUE
2026-09-22 | Tue | Test shoot: light, sound and 9:16 framing. Charge batteries, clear card space, check mics | Shlok | Shoot | Yes |  | OVERDUE
2026-09-22 | Tue | Draft CR01 | Shlok | Design |  |  | OVERDUE
2026-09-22 | Tue | Load the approved scripts into a teleprompter app and print backup copies | Pragaman | Shoot |  |  | OVERDUE
2026-09-23 | Wed | Select the Filing Buddy proof visuals and blur every piece of client personal data | Pragaman | Copy | Yes |  | OVERDUE
2026-09-23 | Wed | Post ST03 | Pragaman | Post |  |  | OVERDUE
2026-09-23 | Wed | Draft ST05 | Shlok | Design |  |  | OVERDUE
2026-09-23 | Wed | Copy ready: VD04 script and CR02 | Pragaman | Copy |  |  | OVERDUE
2026-09-24 | Thu | Main shoot with Anjan, about 3 hours: VD01, VD02a to VD02e, VD07, b-roll | Anjan, Shlok, Pragaman | Shoot | Yes |  | OVERDUE
2026-09-24 | Thu | Log the best take for each clip and back up all footage to Drive before leaving | Shlok | Shoot | Yes |  | OVERDUE
2026-09-24 | Thu | Story poll: Aapke zyada clients kahan se aate hain? Referral / Online | Pragaman | Post |  |  | OVERDUE
2026-09-25 | Fri | Post ST04 | Pragaman | Post |  |  | Today
2026-09-25 | Fri | Finals ST05 and CR01 | Shlok | Design |  |  | Today
2026-09-25 | Fri | Copy ready: ST06 | Pragaman | Copy |  |  | Today
2026-09-28 | Mon | Weekly review 2: first cost per qualified lead by ad, pick the weakest 1 or 2 for the 1 Oct swap | Pragaman | Review | Yes |  | This week
2026-09-28 | Mon | Post ST05 | Pragaman | Post |  |  | This week
2026-09-28 | Mon | Upload this week's grade C leads to NW_CA_EXCL_Blocklist | Pragaman | Ads |  |  | This week
2026-09-28 | Mon | Record VD04 and build the VD01 rough cut | Shlok | Video |  |  | This week
2026-09-29 | Tue | Anjan approves the VD01 rough cut at 5 PM | Anjan | Approval | Yes |  | This week
2026-09-29 | Tue | Draft CR02 | Shlok | Design |  |  | This week
2026-09-29 | Tue | Draft ST06 | Pragaman | Design |  |  | This week
2026-09-30 | Wed | Final VD01 and draft VD04 | Shlok | Video | Yes |  | This week
2026-09-30 | Wed | Post CR01 | Pragaman | Post |  |  | This week
2026-09-30 | Wed | Copy ready: ST07, CR03, CR05 | Pragaman | Copy |  |  | This week
2026-10-01 | Thu | Evening ad change: pause the weakest 1 or 2 ads, add VD01 and CR01 (done today because 2 Oct is a holiday) | Pragaman | Ads | Yes |  | This week
2026-10-01 | Thu | Schedule the VD01 organic post for tomorrow | Pragaman | Post | Yes |  | This week
2026-10-01 | Thu | Finals CR02 (Shlok) and ST06 (Pragaman) | Pragaman, Shlok | Design |  |  | This week
2026-10-01 | Thu | Script ready: VD05 | Pragaman | Copy |  |  | This week
2026-10-01 | Thu | Story poll: Kya aapki firm ki website hai? Haan / Nahi | Pragaman | Post |  |  | This week
2026-10-02 | Fri | Gandhi Jayanti. VD01 posts automatically. Daily check only | Pragaman | Post |  |  | This week
2026-10-05 | Mon | Weekly review 3: replace the starting thresholds with your own averages from two weeks of data | Pragaman | Review | Yes |  | Later
2026-10-05 | Mon | Post ST06 | Pragaman | Post |  |  | Later
2026-10-05 | Mon | Check Instagram Insights for the best posting time and adjust the schedule if needed | Pragaman | Post |  |  | Later
2026-10-05 | Mon | Start the lead-quality ladder if the qualified share is under 50% | Pragaman | Ads |  |  | Later
2026-10-05 | Mon | Final VD04. Start the CR05 and VD02a drafts | Shlok | Video |  |  | Later
2026-10-05 | Mon | Draft ST07 | Pragaman | Design |  |  | Later
2026-10-06 | Tue | Anjan approves ST07, CR05 and VD02a at 5 PM | Anjan | Approval | Yes |  | Later
2026-10-06 | Tue | CR05 and VD02a drafts ready by 12 PM | Shlok | Design |  |  | Later
2026-10-07 | Wed | Post CR02 | Pragaman | Post |  |  | Later
2026-10-08 | Thu | Finals ST07 (Pragaman), CR05 and VD02a (Shlok) | Pragaman, Shlok | Design | Yes |  | Later
2026-10-08 | Thu | Recharge 2: Rs 30,000 | Pragaman | Ads | Yes |  | Later
2026-10-08 | Thu | Story poll: Google pe CA near me search karke dekha hai? Haan / Abhi karta hoon | Pragaman | Post |  |  | Later
2026-10-09 | Fri | Upload the retargeting ads ST07, CR05 and VD02a, scheduled to start 12 Oct | Pragaman | Ads | Yes |  | Later
2026-10-09 | Fri | Post VD04 | Pragaman | Post |  |  | Later
2026-10-09 | Fri | Record the VD05 voiceover | Shlok | Video |  |  | Later
2026-10-11 | Sun | Phase 1 wrap-up: add A and B graded leads to the list, upload NW_CA_LIST_Qualified, build its 1% lookalike | Pragaman | Ads | Yes |  | Later
2026-10-11 | Sun | Create NW_CA_RET_Video50_60d from the CA campaign videos | Pragaman | Ads | Yes |  | Later
2026-10-12 | Mon | Retargeting campaign goes live at Rs 200 a day | Pragaman | Ads | Yes |  | Later
2026-10-12 | Mon | Drop prospecting to Rs 800 a day, swap in the qualified lookalike, exclude the retargeting pools from prospecting | Pragaman | Ads | Yes |  | Later
2026-10-12 | Mon | Post ST07 | Pragaman | Post |  |  | Later
2026-10-12 | Mon | Weekly review 4 | Pragaman | Review |  |  | Later
2026-10-12 | Mon | Draft CR03 | Shlok | Design |  |  | Later
2026-10-13 | Tue | VD05 draft ready by 12 PM | Shlok | Video |  |  | Later
2026-10-13 | Tue | Anjan approves CR03 and VD05 at 5 PM | Anjan | Approval |  |  | Later
2026-10-14 | Wed | Post VD02a | Pragaman | Post |  |  | Later
2026-10-14 | Wed | Final CR03 | Shlok | Design |  |  | Later
2026-10-14 | Wed | Copy ready: ST08 and CR04. Script ready: VD03 | Pragaman | Copy |  |  | Later
2026-10-15 | Thu | Story poll: Aapko kaunse clients zyada chahiye? Retainer / One-time | Pragaman | Post |  |  | Later
2026-10-16 | Fri | Script ready: VD06. Confirm who plays the CA in VD03 and who runs the camera | Pragaman | Copy | Yes |  | Later
2026-10-16 | Fri | Post CR03 | Pragaman | Post |  |  | Later
2026-10-16 | Fri | Final VD05 | Shlok | Video |  |  | Later
2026-10-19 | Mon | VD02b draft by 12 PM. Anjan approves at 5 PM (a day early because tomorrow is Dussehra) | Shlok, Anjan | Approval | Yes |  | Later
2026-10-19 | Mon | Post VD05 | Pragaman | Post |  |  | Later
2026-10-19 | Mon | Weekly review 5, including the first read on retargeting | Pragaman | Review |  |  | Later
2026-10-19 | Mon | Draft ST08 | Shlok | Design |  |  | Later
2026-10-20 | Tue | Dussehra holiday. Daily check only, no edits | Pragaman | Admin |  |  | Later
2026-10-21 | Wed | Post CR05 | Pragaman | Post |  |  | Later
2026-10-21 | Wed | Final VD02b | Shlok | Video |  |  | Later
2026-10-21 | Wed | Shoot VD03, about 1 hour | Shlok | Shoot |  |  | Later
2026-10-22 | Thu | Shoot VD06 with Shlok on camera, about 1 hour | Shlok | Shoot |  |  | Later
2026-10-22 | Thu | Draft CR04 | Shlok | Design |  |  | Later
2026-10-22 | Thu | Story poll: Audit season mein marketing ke liye time milta hai? Bilkul nahi / Thoda | Pragaman | Post |  |  | Later
2026-10-23 | Fri | Post VD02b | Pragaman | Post |  |  | Later
2026-10-23 | Fri | Final ST08 | Shlok | Design |  |  | Later
2026-10-23 | Fri | Copy ready: ST09 | Pragaman | Copy |  |  | Later
2026-10-26 | Mon | Post ST08 | Pragaman | Post |  |  | Later
2026-10-26 | Mon | Weekly review 6 | Pragaman | Review |  |  | Later
2026-10-26 | Mon | Final CR04 and draft VD03 | Shlok | Video |  |  | Later
2026-10-26 | Mon | Draft ST09 | Pragaman | Design |  |  | Later
2026-10-27 | Tue | Drafts VD06, VD02c and VD07, with VD02c and VD07 ready by 12 PM | Shlok | Video |  |  | Later
2026-10-27 | Tue | Anjan approves VD02c and VD07 at 5 PM | Anjan | Approval |  |  | Later
2026-10-28 | Wed | Post CR04 | Pragaman | Post |  |  | Later
2026-10-28 | Wed | Finals VD03 (Shlok) and ST09 (Pragaman) | Pragaman, Shlok | Design |  |  | Later
2026-10-29 | Thu | Final VD06 | Shlok | Video | Yes |  | Later
2026-10-29 | Thu | Story poll: 31 Oct ke baad sabse pehle kya karoge? Chhutti / Naye clients dhoondhna | Pragaman | Post |  |  | Later
2026-10-30 | Fri | Upload the ST09 and VD06 ads, scheduled to start 1 Nov | Pragaman | Ads | Yes |  | Later
2026-10-30 | Fri | Post VD03 | Pragaman | Post |  |  | Later
2026-10-30 | Fri | Final VD02c | Shlok | Video |  |  | Later
2026-10-30 | Fri | Copy ready: ST10 and ST11 | Pragaman | Copy |  |  | Later
2026-10-31 | Sat | Pull the list of leads who asked to be called after the deadline, ready for Monday | Aryan | Leads | Yes |  | Later
2026-10-31 | Sat | Audit-case ITR deadline for CAs. No campaign edits today | Pragaman | Admin |  |  | Later
2026-11-01 | Sun | Deadline switch: pause ST01, and confirm ST09 and VD06 are live | Pragaman | Ads | Yes |  | Later
2026-11-01 | Sun | Post VD06 | Pragaman | Post |  |  | Later
2026-11-02 | Mon | Start calling the after-the-deadline leads from the callback list | Aryan | Leads | Yes |  | Later
2026-11-02 | Mon | Post ST09 | Pragaman | Post |  |  | Later
2026-11-02 | Mon | Weekly review 7 and Phase 2 wrap-up | Pragaman | Review |  |  | Later
2026-11-02 | Mon | Final VD07 | Shlok | Video |  |  | Later
2026-11-02 | Mon | Draft ST11 | Pragaman | Design |  |  | Later
2026-11-03 | Tue | Recharge 3: Rs 30,000, or about Rs 15,000 if the full amount was usable on 17 Sep | Pragaman | Ads | Yes |  | Later
2026-11-03 | Tue | Draft ST10 | Shlok | Design |  |  | Later
2026-11-03 | Tue | Backup slot for Anjan's Diwali wish, only if it was not recorded on 24 Sep | Anjan, Shlok | Shoot |  |  | Later
2026-11-04 | Wed | Post VD02c | Pragaman | Post |  |  | Later
2026-11-04 | Wed | Finals ST10 (Shlok) and ST11 (Pragaman) | Pragaman, Shlok | Design |  |  | Later
2026-11-04 | Wed | Copy ready: CR06 | Pragaman | Copy |  |  | Later
2026-11-05 | Thu | Build the 12 Nov ads as drafts: ST10 in prospecting, and ST03, CR05 and VD02c in retargeting | Pragaman | Ads | Yes |  | Later
2026-11-05 | Thu | Story poll: Kya aapke paas marketing team hai? Haan / Nahi | Pragaman | Post |  |  | Later
2026-11-06 | Fri | Dhanteras. Post ST11 | Pragaman | Post |  |  | Later
2026-11-08 | Sun | Diwali. Post VD07. No campaign edits during festive week | Pragaman | Post |  |  | Later
2026-11-09 | Mon | Stories only, no feed post | Pragaman | Post |  |  | Later
2026-11-09 | Mon | Weekly review 8, read only. Festive week data is not comparable | Pragaman | Review |  |  | Later
2026-11-11 | Wed | Stories only, no feed post | Pragaman | Post |  |  | Later
2026-11-12 | Thu | Final push: publish the 12 Nov ads in both campaigns | Pragaman | Ads | Yes |  | Later
2026-11-12 | Thu | Drafts CR06 and VD02d | Shlok | Design |  |  | Later
2026-11-12 | Thu | Story poll: Instagram se CA firm ko client mil sakte hain? Haan / Doubt hai | Pragaman | Post |  |  | Later
2026-11-13 | Fri | Send Pragaman the top 5 questions CAs asked on calls, for RP01 | Aryan | Copy | Yes |  | Later
2026-11-13 | Fri | Post ST10 | Pragaman | Post |  |  | Later
2026-11-13 | Fri | Final CR06 | Shlok | Design |  |  | Later
2026-11-13 | Fri | Anjan approves VD02d (moved from Tuesday because of Diwali week) | Anjan | Approval |  |  | Later
2026-11-16 | Mon | Post CR06 | Pragaman | Post |  |  | Later
2026-11-16 | Mon | Weekly review 9. Pick the best-performing static to recut as RP02 | Pragaman | Review |  |  | Later
2026-11-16 | Mon | Final VD02d | Shlok | Video |  |  | Later
2026-11-16 | Mon | Copy ready: RP01 | Pragaman | Copy |  |  | Later
2026-11-17 | Tue | RP01 and VD02e drafts by 12 PM | Shlok | Design |  |  | Later
2026-11-17 | Tue | Anjan approves RP01 and VD02e at 5 PM | Anjan | Approval |  |  | Later
2026-11-18 | Wed | Post VD02d | Pragaman | Post |  |  | Later
2026-11-18 | Wed | Final RP01 | Shlok | Design |  |  | Later
2026-11-19 | Thu | Draft RP02 | Shlok | Video |  |  | Later
2026-11-19 | Thu | Story poll: Next tax season ke liye pipeline ready hai? Haan / Abhi nahi | Pragaman | Post |  |  | Later
2026-11-20 | Fri | Post RP01 | Pragaman | Post |  |  | Later
2026-11-20 | Fri | Final VD02e | Shlok | Video |  |  | Later
2026-11-20 | Fri | Copy ready: ST12 | Pragaman | Copy |  |  | Later
2026-11-23 | Mon | Post VD02e | Pragaman | Post |  |  | Later
2026-11-23 | Mon | Weekly review 10. Last creative refresh if frequency is high | Pragaman | Review |  |  | Later
2026-11-23 | Mon | Final RP02 | Shlok | Video |  |  | Later
2026-11-24 | Tue | Draft ST12 | Shlok | Design |  |  | Later
2026-11-25 | Wed | Post RP02 | Pragaman | Post |  |  | Later
2026-11-25 | Wed | Final ST12 | Shlok | Design |  |  | Later
2026-11-26 | Thu | Story poll: Growth ke liye sabse zaroori kya hai? More clients / Better clients | Pragaman | Post |  |  | Later
2026-11-27 | Fri | Post ST12 | Pragaman | Post |  |  | Later
2026-11-30 | Mon | Campaign ends at 11:59 PM | Pragaman | Ads | Yes |  | Later
2026-11-30 | Mon | Export all leads from Meta, all ad data from Ads Manager, and a copy of both trackers | Pragaman | Admin | Yes |  | Later
2026-11-30 | Mon | Stories: thank-you and a DM GROW reminder | Pragaman | Post |  |  | Later
2026-11-30 | Mon | Archive every final creative and all raw footage in the Drive archive folder | Shlok | Admin |  |  | Later
2026-12-07 | Mon | Final campaign report: spend, leads, qualified leads, cost per qualified lead, clients won, ROAS so far | Pragaman | Review | Yes |  | Later
2026-12-07 | Mon | Follow-ups continue with open leads. Keep updating the lead tracker | Aryan | Leads |  |  | Later
2026-12-31 | Thu | ROAS checkpoint: update clients won and 90-day revenue in the lead tracker | Pragaman | Review |  |  | Later
2027-01-31 | Sun | Final ROAS checkpoint and a decision on the next campaign | Pragaman | Review |  |  | Later
Formulas:
Status = IF([Done]="Yes","Done",IF(OR([Done]="Moved",[Done]="Not needed"),[Done],IF([Date]<TODAY(),"OVERDUE",IF([Date]=TODAY(),"Today",IF([Date]<=TODAY()+7,"This week","Later")))))