## Tasks
Task ID | Date | End date | Task | Details / done when | Workstream | Owner | Priority | Status | Stage | Done on | Depends on | Link | Notes | Budget
FBG-01 | 2026-09-28 |  | Remove the old pricing page | No 1,999 anywhere on the site | Website | Pragaman | Normal | Done |  | 2026-09-28
FBG-02 | 2026-09-29 |  | Check the conversion tag on the thank-you page |  | Tracking | Pragaman | Normal | In progress
FBG-03 | 2026-10-01 |  | Approve the launch budget | Budget signed off by Pragaman | Admin | Pragaman | High | Not started | [5 empty] | 50000
FBG-04 | 2026-10-05 | 2026-10-09 | Build the search campaigns | Three campaigns ready to launch | Ads | Pragaman | Normal | In progress | Brief ready |  | FBG-03 |  |  | 30000
FBG-05 | 2026-10-12 | 2026-10-12 | Write the ad copy |  | Copy | Pragaman | Normal |  | Copy ready
FBG-06 | 2026-10-13 | 2026-10-18 | Run the launch week | Daily check of spend and leads | Launch | Pragaman, Riya | High | Not started |  |  | FBG-04
FBG-07 | 2026-10-19 | 2026-10-20 | Review the first week's leads |  | Leads | Pragaman | Normal | Blocked |  |  | FBG-06 |  | Waiting on the CRM export
FBG-08 | 2026-10-14 |  | Design the retargeting banners | Four sizes |  | Creative | Normal | Not started | In review |  |  | https://example.com/banners
FBG-09 | 2026-10-21 |  | Record the explainer video |  | Video | Pragaman | Low | Cancelled |  |  |  |  | Dropped for this launch
FBG-10 | 2026-11-02 | 2026-11-30 | Report on November's leads | Weekly numbers in the report | Reporting | Pragaman | Normal | In progress

## Summary
Tracker summary
Updates by itself from the Tasks tab. Nothing to edit here.
Total tasks | Open | Overdue | Due today | Due next 7 days | Blocked | Done | Completion
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Overdue and due dates use End date for multi-day tasks. Completion = Done / (Total - Cancelled).
By status |  |  |  |  | By workstream
Status | Tasks |  |  |  | Workstream | Open | Done
Not started | 0 |  |  |  | Ads | 0 | 0
In progress | 0 |  |  |  | Creative | 0 | 0
Blocked | 0 |  |  |  | Design | 0 | 0
Done | 0 |  |  |  | Video | 0 | 0
Cancelled | 0 |  |  |  | Copy | 0 | 0
Not started includes tasks with a blank status. |  |  |  |  | Content | 0 | 0
[5 empty] | SEO | 0 | 0
By owner |  |  |  |  | Website | 0 | 0
Owner | Open | Overdue | Due next 7 days | Done | Tracking | 0 | 0
Pragaman | 0 | 0 | 0 | 0 | Leads | 0 | 0
Shlok | 0 | 0 | 0 | 0 | Reporting | 0 | 0
Anjan | 0 | 0 | 0 | 0 | Review | 0 | 0
Aryan | 0 | 0 | 0 | 0 | Approval | 0 | 0
JM | 0 | 0 | 0 | 0 | Launch | 0 | 0
Nehasree | 0 | 0 | 0 | 0 | Admin | 0 | 0
Sharmila | 0 | 0 | 0 | 0
Rows come from the Owner list on the Lists tab (first 12). A task with several owners counts for each.

## Lists
Status | Priority | Owner | Workstream | Stage | How to use this tab
Not started | High | Pragaman | Ads | Brief ready | Yellow cells: edit for this brand. Grey cells: fixed, leave them alone.
In progress | Normal | Shlok | Creative | Copy ready | Owner holds up to 24 names, Workstream up to 29, Stage up to 24.
Blocked | Low | Anjan | Design | Design ready | The Summary tab reports on the first 12 owners and first 20 workstreams.
Done |  | Aryan | Video | In review | Dropdowns on the Tasks tab read from these lists.
Cancelled |  | JM | Copy | Approved
|  | Nehasree | Content | Scheduled
|  | Sharmila | SEO | Posted
Website
Tracking
Leads
Reporting
Review
Approval
Launch
Admin

## Guide
Knit Standard Tracker v1
One tracker format for every brand: Filing Buddy, Noboru, Sapiens, Auxman and whatever comes next. Version 1, 30 Sep 2026.
What to edit
Tab | Edit? | What it is
Tasks | Yes, from row 2 down | Your tasks, one per row. The only tab Knit reads.
Summary | No | Counts that update themselves: open, overdue, due soon, by status, owner and workstream.
Lists | Yellow cells only | Dropdown options for this brand: owners, workstreams, stages. Status and Priority are fixed.
Guide | No | This page. Keep it or delete it in brand copies; Knit ignores it.
Header colours on Tasks: dark navy = required, blue = recommended, light grey = optional. Hover a header to see what goes in it.
Ten rules
1. Row 1 is the header row. Never add title rows above it, and never rename, reorder or delete the 14 standard columns.
2. One task per row: one action, one date, one owner (or a comma list of owners).
3. Date is a real date. Type 30/09/2026 and it shows as Wed 30 Sep 2026. Text like 'next week' or '1-6 Oct' is rejected.
4. Multi-day task: Date is the first day, End date the last. Ongoing work gets an End date too: the day you will review it.
5. Status is always one of five words. Finer pipeline steps (Copy ready, Scheduled) go in Stage, never in Status.
6. Finished: set Status to Done and fill Done on. Not doing it: set Cancelled and say why in Notes. Never delete the row.
7. Blocked means waiting on something outside your control. Say what in Notes.
8. Brand-only columns go to the right of Notes, with a header in row 1. Never insert columns between the standard ones.
9. Keep example and test rows out of Tasks. Anything with a Task is treated as real work.
10. Once Knit connects, it adds Knit Note and a hidden Knit ID at the far right. Never type in them.
The 14 standard columns
Column | Needed | What goes in | Example
Task ID | Recommended | Short unique reference with a brand prefix. Never reused. | FBG-21
Date | Required | Due day, or first day of a multi-day task. A real date. | 30/09/2026 (shows Wed 30 Sep 2026)
End date | Optional | Last day of a multi-day task. Blank for one-day tasks. | 06/10/2026
Task | Required | One action, starting with a verb. | Publish the staged pages
Details / done when | Optional | What done looks like; specs; context. | Site shows ₹2,999 + GST; no 1,999 anywhere
Workstream | Recommended | Type of work, from the Lists tab. | Website
Owner | Required | Who does it, from the Lists tab. Comma for several. | Pragaman, Shlok
Priority | Recommended | High, Normal or Low. High = blocks a launch or someone else. | High
Status | Required | Not started, In progress, Blocked, Done or Cancelled. | In progress
Stage | Optional | Brand pipeline step, from the Lists tab. | Copy ready
Done on | Recommended | Date it was finished. Knit fills it when you mark Done in Knit. | 30/09/2026
Depends on | Optional | Task IDs this waits for. | FBG-20
Link | Optional | One link to the asset or doc. | Canva or Drive link
Notes | Optional | Anything else; the reason when Blocked or Cancelled. | Waiting on the DUNS number
What a filled row looks like
This example lives here on purpose: a row on the Tasks tab would be synced as real work.
Column | Value
Task ID | FBG-21
Date | 30/09/2026 (shows Wed 30 Sep 2026)
End date | (blank: one-day task)
Task | Publish the staged pages
Details / done when | Site shows ₹2,999 + GST; no 1,999 or 5,999 anywhere
Workstream | Website
Owner | Pragaman
Priority | High
Status | Not started
Stage | (blank)
Done on | (blank until finished)
Depends on | FBG-20
Link | (blank)
Notes | (blank)
Status and Stage
Status | Use it when | What Knit does
Not started | Planned, not begun. A blank status counts as this. | Shows it on its date; carries it to the next working day if missed.
In progress | You have started. | Same, and carries In progress forward.
Blocked | Waiting on someone or something else. Say what in Notes. | Keeps it visible and carries it forward, but does not count it as a miss.
Done | Your part is finished. For posts, Scheduled counts as done. | Closes it.
Cancelled | Not doing it. Say why in Notes. | Closes it; it never carries forward.
Stage is for brands with a pipeline, such as a content calendar. A post moves Status In progress + Stage Copy ready, then Stage Design ready, then Status Done + Stage Scheduled. Knit follows Status; Stage is for you and your team.
Dates, weekends and holidays
Put the real date the thing must happen, even if it is a Sunday or a holiday (a Sunday post). Knit shows it on the working day before, so the work is ready in time. Working days are Monday to Friday plus the 1st and 3rd Saturday; holidays come from Knit's holiday list.
Starting a new brand tracker
1. File > Make a copy of this template. Name it '<Brand> · Tracker', for example 'Auxman · Tracker'.
2. Lists tab: fill Owner and Workstream for the brand. Fill Stage only if it has a pipeline; otherwise clear it.
3. Several owners per task? In Google Sheets open Data > Data validation, pick the Owner rule and turn on 'Allow multiple selections'.
4. Add brand-only columns to the right of Notes (Sapiens: Platform, Format, Pillar, Hook, Caption, CTA).
5. When it is ready to sync, move it into the Knit folder in Drive and set it up in Knit.
Moving the current trackers into this format
Tracker | Current column | Goes to | Note
Filing Buddy (Google, Meta) | ID | Task ID | Keep G01 / M01, or prefix FBG-01 / FBM-01.
| Date 'Mon 28 Sep' | Date | Retype as a real date: 28/09/2026.
| Date '1-6 Oct' | Date + End date | Date 01/10/2026, End date 06/10/2026.
| Date 'From 30 Oct' | Date + End date | Date 30/10/2026, End date = the day you will review it.
| Phase | Workstream | Add the phases to the Workstream list.
| Task, Details / done when, Depends on, Notes | Same names | Copy across.
| Owner 'P', 'P + Agent' | Owner 'Pragaman' | Mention the Agent in Notes. Add Creative and Sales to the Owner list.
| Blocks go-live? = Yes | Priority High | Otherwise Normal.
| Status, Done on | Status, Done on | Done on as a real date.
| Ref | Brand column 'Ref' | After Notes.
Noboru CA Campaign | Date, Task, Owner, Notes | Same names | Copy across; keep 'Pragaman, Shlok' style owner lists.
| Day | Delete | The Date cell already shows the weekday.
| Type | Workstream
| Critical path = Yes | Priority High
| Done: Yes | Status Done
| Done: No or blank | Status Not started
| Done: Not needed | Status Cancelled | Reason in Notes.
| Done: Moved | Status Cancelled | Notes: 'Moved to <date>', and add a new row on the new date.
| Status (formula) | Delete | The Summary tab and Knit replace it.
Sapiens Content Calendar | Asset ID | Task ID
| Date | Date | The posting date, even on Sundays.
| Working title | Task
| Status 'Copy ready' and other pipeline words | Status In progress + Stage | Stage holds Copy ready, Design ready, Scheduled.
| Status meaning posted | Status Done + Stage Posted
| Posted on | Done on
| Canva / video link | Link
| Owner, Notes | Same names
| Week, Platform, Format, Pillar, Hook (first line), Caption, CTA, Hashtag set | Brand columns | After Notes, in that order.
| Day | Delete | The Date cell already shows the weekday.